## Sheet1
Date | Risk Description | Likelihood | Impact | Severity (Based on Impact and Likelihood) | Owner | Mitigating Action | Issue Progress
2023-04-08 | Miscommunication with the client regarding project requirements and scope. | Medium | High | High | Project client and project team. | Analysing project demands and requirements using prototypes. | Solved.
2023-07-08 | Scheduling meetings adhering to team members' time commitments | Low | Medium | Low | Project team. | Team member voting to pick a suitable weekday for everyone to meet and discuss. | Solved. (Weekday fixated that everyone agrees to)
Week 2 | Increased difficulty in team time commitments due to other assignments | Medium | High | High | Project team. | Dividing personal assignments and cits3200 project into various subsections and implementing proper scheduling. | Ongoing.
Week 2 | Design and implementation decisions Incomplete | Medium | Medium | Medium | Project team. | Consult appropriate knowledge bases to decide the technologies that will be used in implementation. | Solved.
Week 3 | Project development process slower than optimal. | Medium | High | Medium | Project team. | Implement proper scheduling and assigning of tasks so every member gets the work done by the nominated deadline. | Partially solved. Partially ongoing.
Upcoming | Risk in using React - lack of people who have used it in the past. | Medium | Medium | Medium | Project team. | Training must be accounted for in schedules, people with react knowledge should teach and mentor new users | Ongoing.